## Group A Migration Plan
Institution | Date and time migration | IDC on duty | Software development on duty | Request a window of 10 hours to complete per day
Ministry of ICT and Innovation | 2019-06-01 20:00 | Brice Veronique
Institution | Start of migration | IDC on duty | Software development on duty
RwandaMilitaryHospital | 2019-06-14 20:00 | Placidie Solange
NationalWomenCouncil
SpecialGuaranteeFund
RwandaElders
RwandaStockExchange
Institution | Start of migration | IDC on duty | Software development on duty
MediaHighCouncil | 2019-06-15 20:00 | Veronique
NationalCommissionofScienceandTechnology
RwandaNationalInvestmentTrust
Institution | Start of migration | IDC on duty | Software development on duty
CapitalMarketAuthority | 2019-06-16 20:00 | Solange
RoadMaintenanceFund
Institution | Start of migration | IDC on duty | Software development on duty
Local Development Agency | 2019-06-17 20:00 | Brice

## Group B Migration Plan
Institution | Start of migration | IDC on duty
Agaciro Development Fund | 2019-06-18 20:00 | Placidie | Request a window of 10 hours to complete per day
The National Council of Person with Disabilities
Inteko Nyarwanda y’Ururimi n’Umuco
Institution | Start of migration | IDC on duty
National Commission fo Children | 2019-06-19 20:00 | Veronique
Rwanda Management Institute
Institution | Start of migration | IDC on duty
Gender Monitoring Office | 2019-06-20 20:00 | Solange
Public Service Commission
Rwanda Public Procurement Authority
Institution | Start of migration | IDC on duty
National Unity and Reconcilitation Commission | 2019-06-21 20:00 | Brice
Institution | Start of migration | IDC on duty
Higher Education Council | 2019-06-22 20:00 | Placidie
Institution | Start of migration | IDC on duty
National Youth Council | 2019-06-22 20:00 | Veronique
Institution | Start of migration | IDC on duty
Ministry of Gender and Family Promotion | 2019-06-23 20:00 | Solange

## Group C Migration Plan
Institution | Start of migration | IDC on duty
Rwanda Meteorology Agency | 2019-06-24 20:00 | Placidie | Request a window of 10 hours to complete per day
Institution | Start of migration | IDC on duty
Rwanda Demobilization and Reintegration commission | 2019-06-25 20:00 | Veronique
Southernprovince
Rwanda Mines, petroleum and Gas Board
Rwanda Water and Forestry Authority
Military Medical Insurance
Institution | Start of migration | IDC on duty
Ministry of Loval Government | 2019-06-26 20:00 | Solange
Institution | Start of migration | IDC on duty
City of Kigali | 2019-06-27 20:00 | Brice
Institution | Start of migration | IDC on duty
Ministry of Public Service and Labour | 2019-06-28 20:00 | Placidie
Institution | Start of migration | IDC on duty
Rwanda law reform commission | 2019-06-29 20:00 | Veronique